## Overall (with%prog)
|  | 2016 | [6 empty] | 2017 | 2018 | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 - 12 | 1 - 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 - 3 |  | 4 - 6 |  | 7 - 9 |  | 10-12
|  | Before COVID-19 | [8 empty] | 3: COVID-19 Pandemic; 12: Force Majeure (FM); 7: 2nd Outbreak
EPCI Contract Key Dates
CONTRACT VALUE TRANSFORMATION | ORIGINAL |  |  |  | LUMP SUM 2,396 MUSD
PROV SUM 36 MUSD
| AMD-2 |  |  |  | LUMP SUM (incl.LOGI) | [5 empty] | 5: LUMP SUM (excl.LOGI); TOTAL LUMP SUM 2,667 MUSD; 11: FGRS RCE 188 MUSD; 9: Demobilization
PROV SUM 36 MUSD
LOGI RCE 250 MUSD
| AMD-3 |  |  |  | LUMP SUM (incl.LOGI) | [5 empty] | 5: LUMP SUM (excl.LOGI); TOTAL LUMP SUM 2,643 MUSD; 9: FGRS RCE 421 MUSD; 4: Demobilization
LOGI RCE 310 MUSD
PROV SUM 273 MUSD (incl. COVID Response 236 MUSD)
Backcharge on Fuel Equipment -20 MUSD
| AMD-4 |  |  |  | LUMP SUM (incl.LOGI) | [5 empty] | 5: LUMP SUM (excl.LOGI); TOTAL LUMP SUM 2,643 MUSD; 9: FGRS RCE 854 MUSD; 12: Demobilization | [8 empty] | 2016-08-26
[11 empty] | 5: LOGI RCE 342 MUSD | [8 empty] | 2020-06-26
PROV SUM 445 MUSD (incl. COVID Response 408 MUSD)
Backcharge on Fuel Equipment -20 MUSD
| AMD-5 |  |  |  | LUMP SUM (incl.LOGI) | [5 empty] | 5: LUMP SUM (excl.LOGI); TOTAL LUMP SUM 2,643 MUSD; 9: FGRS RCE 1,510 MUSD; 7: Demobilization
LOGI RCE 447 MUSD
PROV SUM 467 MUSD (incl. COVID Response 420 MUSD)
Backcharge on Fuel Equipment -20 MUSD
| Post AMD-5 |  |  |  | LUMP SUM (incl.LOGI) | [5 empty] | 5: LUMP SUM (excl.LOGI); TOTAL LUMP SUM 2,643 MUSD; 9: FGRS RCE 1,830 MUSD
LOGI RCE 479 MUSD
PROV SUM 478 MUSD (incl. COVID Response 420 MUSD)
Backcharge on Fuel Equipment -20 MUSD
FGRS RCE ACTUAL COST (MUSD) | Monthly FGRS | [29 empty] | 30.9822 | 43.6446 | 39.3792 | 18.9942 | 6.0915 | 15.3404 | 30.9037 | 37.3978 | 40.0561 | 36.6476 | 19.8232 | 19.7288 | 32.2243 | 40.7959 | 44.945 | 44.9286 | 54.1167 | 55.0453 | 63.6219 | 56.2193 | 60.4038 | 64.216 | 70.561 | 74.2649 | 84.3162 | 63.1108 | 67.4946 | 65.4731 | 43.2187 | 42.671 | 45.0574 | 45.7958 | 38.1297 | 45.1744 | 39.5462 | 25.5767 | 22.953 | 18.5404 | 27.9157 | 24.0577 | 137.3576
| AMD-3 Est.Period | [9 empty] | 9: FGRS RCE 675 MUSD
| AMD-4 Est.Period | [9 empty] | 9: FGRS RCE 1215
| AMD-5 Est.Period | [9 empty] | 9: FGRS RCE 1,541
| Post AMD-5 | [9 empty] | 9: Cummulative FGRS RCE (VOWD+ETC): 1,837
LOGI RCE ACTUAL COST (MUSD) | Monhtly LOGI | [13 empty] | 15.5064 | 33.9983 | 54.47 | 76.816 | 100.3709 | 124.3829 | 145.5246 | 167.155 | 186.663 | 205.1683 | 221.8566 | 234.1767 | 242.2351 | 250.9905 | 257.5128 | 262.793 | 271.7151 | 276.0313 | 282.7341 | 287.6285 | 291.3234 | 295.2016 | 300.1043 | 304.2904 | 309.0379 | 312.9942 | 317.0333 | 320.9884 | 324.7843 | 328.1075 | 333.015 | 337.185 | 341.6393 | 346.5465 | 351.0386 | 355.4068 | 360.5549 | 364.5682 | 368.587 | 372.3528 | 377.396 | 381.5854 | 385.9058 | 390.2703 | 394.7417 | 399.3178 | 403.6695 | 406.5956 | 410.7717 | 414.7493 | 418.4999 | 422.2413 | 425.6643 | 429.4673 | 434.2991 | 438.9036 | 42.7639
| AMD-3 Est.Period | [9 empty] | 5: LOGI RCE 351 MUSD
| AMD-4 Est.Period | [9 empty] | 5: LOGI RCE 386 MUSD
| AMD-5 Est.Period | [9 empty] | 5: LOGI RCE 415 MUSD
| Post AMD-5 | [9 empty] | 5: Cummulative LOGI RCE (VOWD+ETC): 482 MUSD
POB (CSTS+SubCon) | [17 empty] | 9133 | 9972.1333 | 10555.4 | 10951.2667 | 12071.2 | 12414.4667 | 11877.7667 | 11257.8333 | 5684.3667 | 6474.8667 | 6526.7 | 7439.9333 | 7864.9 | 7460.9667 | 7805.5 | 8254.6333 | 4923.8 | 1227.6 | 1884.6333 | 4833.4667 | 6836.4 | 7837.7 | 7753.4 | 7552.6 | 6713.4667 | 6503.9 | 8689.8 | 9834.0667 | 10538.5 | 10732.6333 | 10199.3667 | 11496.3667 | 11440.2 | 12123.6 | 11617.9667 | 12296.6 | 12470.8333 | 12095.6 | 11726.3333 | 9867.4667 | 8364.0333 | 7036.6667 | 5775.2667 | 5970.3 | 5140.6 | 4997.7333 | 4352.9333 | 3707.0333 | 2559.3667 | 2186 | 2096.2333 | 2057.7333 | 1979.0333
Workers at Site Isolation Facility | [10 empty] | 3: 22; 4: 34; 5: 57; 6: 303; 7: 459; 8: 520; 9: 386; 10: 1170; 11: 385; 12: 216
KEY HIGHLIGHTS | [10 empty] | 3: - Indonesia declared COVID-19 pandemic in March 2020. - As a response, Site POB was restricted to 6,300 and continue with a ramp-up. - POB was capped with max. of 7,700 (as basis for AMD-3) - Project activities (especially critical ones) continued to run at a slower pace due to reduced POB. - Project had difficulties to moblize supervisor to Site due to restriction by regulation to enter Indonesia or travel within the country. - Preservation works.; 12: - 1st Outbreak at Site (Alfa variant). - Mass demobilization. - Main project activities stopped with 0% progress. - Continue preservation works.; 3: - Slow POB ramp-up limited by the logistical capability. Implement quarantine prior to Site. - Flight restriction by regulation. - Project had difficulties to control the right composition of workers and supervision due to many workers infected by the virus. - Continue preservation works.; 7: - 2nd Outbreak Site (Delta variant) with 0% progress in Jul-Aug'21. - Main project activities stopped due to most of the workers were in isolation. - 3rd Outbreak was in Oct-21 (Omicron variant) which forced progress continued with lower pace. - Vaccination program at Site. - Jul-Oct'21: Ceramic bolt replacement.; 11: - Considering the phase of project with 90% progress and majority of remaining activities are required to be in-sequence (commissioning), hence its resulting average plan progress per month of 0.4%. - Finishing activities found there were reworks required – additional resources mobilized to minimize the impact on base activities. - Sep-Nov'22: Permali blocks replacement. - Feb-Apr'23: Inconel bolts replacement.
PIPING ERECTION CASE:
Meindo | Subcontract Duration and Value
| Achieved Mhrs | [12 empty] | 14.528 | 16.083 | 24.561 | 7.161 | 0 | 2.545 | 5.98 | 39.89 | 1186.75 | 86.4 | 144.642 | 6835.677 | 0.144 | 0 | 0 | 1197.044 | 4652.831 | 1681.217 | 131 | 0 | 0 | 0 | 0 | 15949.584 | 397.789 | 12.019 | 297.561 | 163.235 | 0 | 492.429 | 156.345 | 3071.644 | 95.309 | 0 | 0 | 0 | 0 | 0 | 0 | 16.366 | 0 | 17.279 | 2.568 | 20.919 | 79.08 | 1.524 | 0.289 | 2.598 | 0 | 0 | 0
| Invoice Value (MUSD) | [9 empty] | 10: 0.73952; 11: 1.2114; 12: 0; 1: 0.23732; 2: 0; 3: 0; 4: 0.60651; 5: 0; 6: 0; 7: 0; 8: 2.6232; 9: 0.20468; 10: 0.21958; 11: 0.44227; 12: 0.17584; 1: 1.5385; 2: 3.0342; 3: 0; 4: 0.86559; 5: 0.88169; 6: 1.2138; 7: 0.79725; 8: 1.0383; 9: 1.9807; 10: 0; 11: 0.40263; 12: 0.30864; 1: 0.52458; 2: 0; 3: 0.15793; 4: 0; 5: 0; 6: 0; 7: 0.69626
| Actual/VOWD | [29 empty] | 0.23678 | 0.1102 | 0.28449 | 0.22252 | 0 | 0 | 0 | 0.41572 | 0.84691 | 0.72159 | 0.68623 | 0 | 0.1457 | 0.18845 | 0.36039 | 0.13942 | 1.11 | 2.7168 | 0.71205 | 0.61247 | 0.99612 | 2.3067 | 0.8801 | 0.70877 | 0.87626 | 0.30695 | 0.22442 | 0.83637 | 0.30277 | 0 | 0.070308 | 0.054781 | 0 | 0 | 0.77773 | 0 |  | - Total VOWD (Sep'20 to Sep'23): 17.85 MUSD - SC Value: 48.6 MUSD (final value subject to close out) BP only pay 17.8 MUSD out of 48.6 MUSD SC value. | [9 empty] | 17.8511 | up to Sep'23
| POB | [16 empty] | 265 | 296.1667 | 497.2667 | 543.6333 | 766.8667 | 768.0333 | 712.5333 | 594.1667 | 64.8667 | 90.5333 | 184 | 243.5333 | 254.9667 | 220.3333 | 251.4333 | 452.3 | 251.8 | 13.6333 | 16.4667 | 95.5 | 205.9333 | 329.5 | 391.2333 | 405.2333 | 273.7667 | 239.9 | 372.0667 | 692 | 814.7333 | 788.9 | 768.7333 | 950.6667 | 884.3667 | 952.9667 | 926.9 | 929.6667 | 804.4667 | 789.4667 | 725.8333 | 506.4333 | 372.9 | 225.7333 | 135.5333 | 147.4667 | 104.7667 | 39.6667 | 16.5
| Plan Cumm.Prog | [12 empty] | 0% | 0% | 0.7505% | 2.163% | 4.996% | 8.304% | 13.1% | 22.77% | 29.55% | 36.54% | 45.44% | 50.9% | 51.43% | 51.59% | 52.25% | 52.47% | 57.96% | 59.18% | 62.07% | 64.29% | 71.69% | 71.7% | 71.8% | 71.8% | 71.9% | 72% | 72.1% | 72.2% | 72.27% | 75.39% | 75.5% | 75.6% | 75.74% | 84.47% | 90.44% | 93.82% | 97.63% | 98.88% | 99.2% | 99.61% | 99.77% | 99.97% | 99.97% | 99.97% | 99.97% | 99.98% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Actual Cumm. Prog | [12 empty] | 0% | 0% | 0.002628% | 0.01862% | 0.3487% | 1.93% | 5.26% | 13.27% | 23.25% | 33.43% | 45.04% | 52.09% | 52.1% | 52.11% | 52.86% | 58.18% | 58.57% | 59.49% | 62.52% | 64.82% | 64.99% | 64.99% | 64.99% | 65.1% | 65.2% | 65.5% | 65.8% | 66% | 67% | 68% | 69% | 71.94% | 74.5% | 79.27% | 84.34% | 88.03% | 92.97% | 95.5% | 97.01% | 97.77% | 98.27% | 99.03% | 99.19% | 99.3% | 99.55% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Plan per Month | [12 empty] | 0% | 0% | 0.7505% | 1.413% | 2.833% | 3.308% | 4.796% | 9.666% | 6.782% | 6.996% | 8.9% | 5.451% | 0.5352% | 0.1591% | 0.6633% | 0.217% | 5.49% | 1.217% | 2.888% | 2.225% | 7.399% | 0.01076% | 0.1% | 0% | 0.1% | 0.1% | 0.1% | 0.1% | 0.06892% | 3.124% | 0.1074% | 0.1% | 0.1373% | 8.732% | 5.968% | 3.386% | 3.808% | 1.25% | 0.3217% | 0.4063% | 0.1606% | 0.1999% | 0.000847% | 0.000135% | 0% | 0.006156% | 0.01241% | 0.008351% | 0.002152% | 4.897e-05% | 0% | 0% | 0% | 0%
| Actual per Month | [12 empty] | 0% | 0% | 0.002628% | 0.01599% | 0.3301% | 1.581% | 3.33% | 8.012% | 9.983% | 10.18% | 11.6% | 7.058% | 0.002218% | 0.01182% | 0.7488% | 5.322% | 0.3957% | 0.9148% | 3.028% | 2.299% | 0.1694% | 0% | 0% | 0.1137% | 0.1% | 0.3% | 0.3% | 0.2% | 1% | 1% | 1% | 2.938% | 2.563% | 4.768% | 5.076% | 3.688% | 4.939% | 2.531% | 1.509% | 0.7631% | 0.491% | 0.7602% | 0.166% | 0.1061% | 0.2537% | 0.4392% | 0.0068% | 0.0003155% | 0.001448% | 5.643e-05% | 0% | 0.0004342% | 7.443e-09% | 0%
[26 empty] | - Preservation works - Piping reworks/repair | [7 empty] | No progress means no major activities performed. |  |  |  | - Preservation works - Piping reworks/repair | [8 empty] | - Piping works at the completion phase, most of the works is smail dia-inches and in average 30% of the crew allocated for piping reworks - Piping reworks/repair
Penta | Subcontract Duration and Value | [73 empty] | - Total VOWD (up to Sep'24): 49.35 MUSD - SC Value: 69.9 MUSD (final value subject to close out) BP only pay 49.3 MUSD out of 69.9 MUSD SC value.
| Achieved Mhrs | [12 empty] | 0 | 0 | 1946 | 5.893 | 2.533 | 2.116 | 50.794 | 24.116 | 10.446 | 568.017 | 147.849 | 2639.476 | 1701.214 | 934.598 | 60.488 | 1882.803 | 3563.55 | 1552.291 | 106 | 0 | 0 | 0 | 0 | 0 | 246.666 | 102.165 | 22.492 | 189.808 | 0 | 45.169 | 43.489 | 90.22 | 534.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.781 | 0.542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Invoice Value (MUSD) | [9 empty] | 9: 0.60099; 10: 1.7672; 11: 0; 12: 0.95793; 1: 0; 2: 0; 3: 0; 4: 0.77736; 5: 0.48934; 6: 0.12364; 7: 0; 8: 0; 9: 0; 10: 0.34067; 11: 1.1635; 12: 1.0254; 1: 0.8535; 2: 1.3184; 3: 1.3989; 4: 1.7374; 5: 1.3184; 6: 0.5161; 7: 1.7033; 8: 1.2421; 9: 5.4427; 10: 2.2765; 11: 1.6482; 12: 0; 1: 0; 2: 2.6334; 3: 1.2902; 4: 0.66209; 5: 0.99902; 6: 0; 7: 1.8348
| Actual/VOWD | [29 empty] | 0.6004 | 1.6154 | 1.4157 | 0 | 0 | 0 | 0 | 1.2503 | 0.94711 | 0.58141 | 0 | 0 | 0 | 1.0419 | 1.3807 | 1.0254 | 0.8535 | 1.3989 | 1.7374 | 1.3184 | 1.8345 | 1.7033 | 2.5605 | 3.3825 | 10.1511 | 2.6956 | 2.5164 | 1.427 | 0.65765 | 0.60867 | 0.66209 | 0.99902 | 0.6135 | 0.60779 | 0.62484 | 0.40682 | 0 | 0.37379 | 0.36976 | 0.36006 | 1.6271 | [6 empty] | 49.3485 | up to Sep'23
| POB | [16 empty] | 225 | 239.2667 | 292 | 413.7 | 535.4667 | 574.8667 | 652 | 632.7 | 362.6333 | 396.3667 | 367 | 544.3667 | 625.7 | 578.4 | 614.5 | 670.6 | 289.3667 | 7.3667 | 31.6667 | 359.8 | 585.4 | 644.4333 | 630.7667 | 552.5 | 460.0667 | 410.7333 | 725.1667 | 880.0667 | 813.5667 | 723.6667 | 718.5 | 737.9667 | 739.9333 | 751.5333 | 638.1 | 629.1 | 584.7333 | 509.5333 | 392.9 | 209.7333 | 171.5 | 111.9 | 98.4333 | 111.3667 | 103.3667 | 103.5 | 94.3 | 91.2 | 50.2333 | 39.2 | 41.2333 | 39.5 | 37.7667
| Plan Cumm.Prog | [12 empty] | 0% | 0.04901% | 1.772% | 4.012% | 7.14% | 9.796% | 12.46% | 17.26% | 19.96% | 22.61% | 25.84% | 37.98% | 41.28% | 45.04% | 47.11% | 51.35% | 69.14% | 69.18% | 69.95% | 71.72% | 76.85% | 77% | 77.5% | 78% | 78.5% | 79% | 79.76% | 79.9% | 80% | 80.1% | 80.26% | 81.15% | 86.49% | 94.49% | 98.31% | 99.85% | 99.98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Actual Cumm. Prog | [12 empty] | 0% | 0.006442% | 0.4323% | 1.411% | 2.937% | 4.721% | 6.532% | 10.62% | 15.54% | 20.26% | 25.55% | 36.14% | 39.49% | 43.85% | 48.71% | 59.6% | 71.23% | 71.31% | 74.44% | 74.6% | 74.7% | 74.8% | 74.9% | 75% | 75.13% | 76.5% | 77.24% | 77.68% | 77.68% | 78.09% | 79% | 80.91% | 84.19% | 87.97% | 91.83% | 94.36% | 97% | 98.2% | 99.12% | 99.59% | 99.77% | 99.93% | 99.97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Plan per Month | [12 empty] | 0% | 0.04901% | 1.723% | 2.24% | 3.129% | 2.655% | 2.662% | 4.799% | 2.703% | 2.646% | 3.24% | 12.14% | 3.294% | 3.768% | 2.062% | 4.241% | 17.79% | 0.04004% | 0.7694% | 1.777% | 5.125% | 0.1527% | 0.5% | 0.5% | 0.5% | 0.5% | 0.7618% | 0.1382% | 0.1% | 0.1% | 0.1634% | 0.8887% | 5.34% | 7.998% | 3.822% | 1.537% | 0.131% | 0.01686% | 0.002291% | 6.27e-06% | 8.733e-05% | 0.0001649% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Actual per Month | [12 empty] | 0% | 0.006442% | 0.4259% | 0.9783% | 1.527% | 1.783% | 1.811% | 4.085% | 4.923% | 4.724% | 5.285% | 10.59% | 3.357% | 4.361% | 4.853% | 10.89% | 11.63% | 0.08123% | 3.13% | 0.1624% | 0.1% | 0.1% | 0.1% | 0.1% | 0.134% | 1.364% | 0.7423% | 0.4385% | 0% | 0.4083% | 0.9125% | 1.908% | 3.281% | 3.779% | 3.863% | 2.533% | 2.633% | 1.198% | 0.9216% | 0.4719% | 0.183% | 0.1567% | 0.04495% | 0.02635% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[15 empty] | Penta not performing as per plan due to a combination of reasons: workfront availability (steel structure erection was late) hence impacting productivity as well | [10 empty] | Penta is prioritizing the large DI pipe once the workfront is available | [7 empty] | No progress means no major activities performed. |  |  |  | Piping reworks/repair | [8 empty] | - Piping works at the completion phase, most of the works is smail dia-inches and in average 30% of the crew allocated for piping reworks - Piping reworks/repair
[13 empty] | Contract Rev.0; Mar-2019 - Nov-2020 (21 months) | [20 empty] | Contract Rev.1 and Rev.2; Dec-2019 - Oct-2022 (22 months extension) | [22 empty] | Contract Rev.3 (extension up to May-2023) --> Contract Rev.4 (up to Oct-2023) --> Contract Rev.5 (up to May-2024) (Total 20 monthts)
Contract is effective before start of the reimbursable period (1-Sep-20)
[45 empty] | Extension to complete remaining scope. | [25 empty] | Extension to complete remaining scope and additional various activities. Compensation changed to time rate (timesheet) basis in Contract Rev.3
Compensation: Unit Price basis
[45 empty] | 1) Reflect actual progress payment as of Contract rev.1, reduced scope, and some settlement claim between Penta and CSTS. | [25 empty] | 1) No change since Contract Rev.2 up to Rev.5
[45 empty] | 2) Settlement claim due to COVID-19 impact, such as reduced POB, and time for remobilisation after COVID outbreaks. | [25 empty] | 2) No change since Contract Rev.1
[45 empty] | 3) To stimulate increment of productivity, efficiency, quality of work and safety. The criteria invcludes achievement of milestones by monthly and by system, and zero safety incident. | [25 empty] | 3) No change since Contract Rev.1
4) No change since Contract Rev.1
4) Manpower standby due to work interruption in Feb and Oct-20; and flight cancellation.
[45 empty] | 5) Compensation as per PP No.35/2021 upon expiration of employment agreement. Payment from bp to CSTS is based on actual payment made by Subcontractor to workers. | [25 empty] | 5) Compensation as per PP No.35/2021 upon expiration of employment agreement. Payment from bp to CSTS is based on actual payment made by Subcontractor to workers.
[45 empty] | 6) - Backcharges are additional services provided by CSTS to support Subcontractor. - CWO includes supply of equipment and operator, manpower supply and other required supports. | [25 empty] | 6) Value decreases due to inclusion of additional CWO such as support to other Subcontractors at ORF area, equipment supply, temporary spools fabrication, etc.
7) Reflect latest estimate. Provisional to cover COVID-19 related cost e.g., standby cost during outbreaks.
7) Provisional to cover COVID-19 related cost e.g., standby cost during outbreaks.
8) Supply of manpower and equipment from Nov'22 - May'24 for various activities outside its original scope e.g.,: modification works, reinstatement, red spade and spools removal, ceramic bolt replacement, punch close-out, shelter demolition, etc.
9) Manpower supply to support Start-Up activity.
[11 empty] | 9: TOTAL payment from 1 Sep'20: |  |  | 49348
in thousand USD
Daewoo (Contract No. 1306754 1306984) | Subcontract Duration and Value
| Achieved Mhrs | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6.234 | 47.427 | 26.578 | 1.203 | 819.852 | 4045.236 | 2955.531 | 1036.042 | 4047.313 | 1858.213 | 1481.137 | 1755.763 | 206 | 0 | 0 | 0 | 0 | 0 | 1056.94 | 302.568 | 321.062 | 16.908 | 0 | 182.126 | 85.525 | 1904.729 | 600.455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.407 | 0.465 | 7.037 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Invoice Value (MUSD) | [9 empty] | 9: 2.6836; 10: 3.9369; 11: 3.5079; 12: 0.42872; 1: 0.88331; 2: 0; 3: 2.5964; 4: 3.6365; 5: 4.6287; 6: 0.40462; 7: 0.14871; 8: 0; 9: 4.7473; 10: 0.90799; 11: 0; 12: 6.2563; 1: 4.4734; 2: 4.3723; 3: 9.1466; 4: 10.6413; 5: 5.8916; 6: 5.993; 7: 4.8636; 8: 8.3797; 9: 9.8243; 10: 0.84879; 11: 8.6736; 12: 5.323; 1: 4.6189; 2: 0; 3: 2.4647; 4: 4.8703; 5: 1.072; 6: 3.3443; 7: 0.72297
| Actual/VOWD | [29 empty] | 2.3003 | 4.3304 | 3.8485 | 1.5071 | 0 | 0.47234 | 2.5308 | 3.6145 | 5.0608 | 3.2273 | 1.7219 | 0.79756 | 3.434 | 3.1064 | 4.2302 | 4.7368 | 4.6708 | 4.4268 | 10.2036 | 5.3073 | 6.5933 | 5.702 | 5.8489 | 8.883 | 9.1464 | 3.8421 | 4.6544 | 5.8249 | 1.146 | 0.86693 | 2.0621 | 2.3702 | 0.85652 | 3.8411 | 0.18831 | 0 |  |  | - Total VOWD (up to Jul'23): 131.35 MUSD - SC Value: 179.1 MUSD (final value subject to close out) BP only pay 131.3 MUSD out of 179.1 MUSD SC value. | [8 empty] | 131.3534 | up to Sep'23
| Plan POB | [9 empty] | 12: 47; 1: 228; 2: 269; 3: 334
| Actual POB | [14 empty] | 6 | 6 | 6 | 6 | 10.3333 | 11.3333 | 39 | 189.5 | 448.6667 | 569.6667 | 526.9333 | 534.3667 | 512 | 521.5 | 537.4 | 556.2 | 601 | 599.3333 | 526.5333 | 42.5333 | 151.8333 | 421.2667 | 611.0667 | 731.9667 | 722.4667 | 745.7333 | 727.9 | 701.9667 | 730.1 | 831 | 942.3667 | 971.7333 | 880.9667 | 999.8 | 1027.4333 | 1080.2667 | 1038.3333 | 1166.1333 | 1148.4333 | 1032.5333 | 889.2 | 489.6333 | 274.1 | 209 | 159.7333 | 146.4 | 112.4333 | 106.4333 | 74.1333 | 9.2105 | 1
| Plan Cumm.Prog | [12 empty] | 0% | 0.1632% | 4.362% | 4.991% | 7.093% | 11.84% | 12.3% | 12.59% | 12.76% | 14.9% | 17.74% | 39.76% | 44.04% | 48.51% | 50.45% | 53.12% | 66.67% | 66.9% | 67.57% | 72.16% | 75.25% | 81.78% | 81.9% | 82% | 82.2% | 82.4% | 82.45% | 85.46% | 88.19% | 88.4% | 88.53% | 88.82% | 90.36% | 93.26% | 96.85% | 99.22% | 99.94% | 99.97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Actual Cumm. Prog | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 1.243% | 3.588% | 5.797% | 8.474% | 17.46% | 27.69% | 34.55% | 44.58% | 54.06% | 62.01% | 68.99% | 71.9% | 77.92% | 85.3% | 85.32% | 85.32% | 85.33% | 85.7% | 86.5% | 86.7% | 86.9% | 87.49% | 87.49% | 87.77% | 87.9% | 88.95% | 90.53% | 93.39% | 96.75% | 97.53% | 98.64% | 99.3% | 99.64% | 99.7% | 99.78% | 99.91% | 99.97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Plan per Month | [12 empty] | 0% | 0.1632% | 4.199% | 0.6281% | 2.102% | 4.743% | 0.4683% | 0.2836% | 0.1767% | 2.131% | 2.844% | 22.02% | 4.282% | 4.466% | 1.942% | 2.668% | 13.54% | 0.2299% | 0.6787% | 4.59% | 3.091% | 6.527% | 0.1184% | 0.1% | 0.2% | 0.2% | 0.05224% | 3.008% | 2.728% | 0.2121% | 0.1286% | 0.2927% | 1.536% | 2.906% | 3.585% | 2.372% | 0.7139% | 0.03074% | 0.03424% | 0% | 0% | 5.226e-07% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Actual per Month | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 1.243% | 2.346% | 2.209% | 2.676% | 8.985% | 10.23% | 6.853% | 10.03% | 9.48% | 7.954% | 6.975% | 2.91% | 6.025% | 7.382% | 0.01885% | 0% | 0.006906% | 0.3717% | 0.8% | 0.2% | 0.2031% | 0.5868% | 0% | 0.2771% | 0.1331% | 1.053% | 1.574% | 2.867% | 3.351% | 0.7833% | 1.116% | 0.6544% | 0.3383% | 0.0593% | 0.08391% | 0.1258% | 0.06368% | 0.03044% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[15 empty] | Daewoo not performing as per plan due to a combination of reasons: workfront availability (steel structure erection was late) hence impacting productivity as well | [10 empty] | Daewoo is prioritizing the large DI pipe once the workfront is available | [7 empty] | No progress means no major activities performed. |  |  |  | Piping reworks/repair | [8 empty] | - Piping works at the completion phase, most of the works is smail dia-inches and in average 30% of the crew allocated for piping reworks - Piping reworks/repair
[21 empty] | USD PORTION | Contract Rev.0; Dec-2019 - Mar-2021 (16 months) | [15 empty] | Contract Rev.1; Dec-2019 - Oct-2022 (19 months extension) | [18 empty] | Contract Rev.2; Dec-2019 - Jun-2023 (8 months extension)
Contract is effective before start of the reimbursable period (1-Sep-2020)
[47 empty] | Extension to complete remaining scope. | [20 empty] | Extension to complete remaining and additional scope.
[29 empty] | Compensation: |  | Time Rate basis (timesheet) | [15 empty] | Estimated Total Personnel: |  |  |  | 1191
[47 empty] | 1) -Include Fabrication, Testing, Storing of Temporary Spool (27ea) for commissioning activity. - Include additional scope related to Train 3 Warm Section Area and Degreasing | [20 empty] | 1) Include inconnel bolt replacement, commissioning support, KIV modification/installation, leak test support, mechanical support incl. punch clearance.
[29 empty] | No. of Personnel: |  | 552
[29 empty] | 2) Mobiisation cost based on USD 10,600/person | [17 empty] | 2) - Include additional mobilisation of 205 personnel to cover the additional warm scope - Change mobilisation cost from USD 10,600/person to cost plus fee (10%)
2) Reflect actual spend + estimated to complete
[29 empty] | 3) Milestone for Cold Section of Train-3 area. | [17 empty] | 3) Revise Miltestone with additional of USD 2,650 K for the additional scope | [20 empty] | 3) No change
[47 empty] | 4) Additional services for WPS and WQT from Migas (cost plus fee 10%) | [20 empty] | 4) Reflect actual spend
[47 empty] | 5) To stimulate increment of productivity, efficiency, quality of work and safety. The criteria includes completion of 4 system reinstatements, achievement of test pakacges, and zero safety incident. | [20 empty] | 5) Increase to reflect the actual incentive payment
[47 empty] | 6) Separate incentive for night workers for the same purpose above. | [20 empty] | 6) Decrease to reflect the actual incentive payment
[47 empty] | 7) Additional services to provide OPITO Training for banksman/riggers (cost plus fee 10%) | [20 empty] | 7) No change
8) Provisional to cover COVID-19 related cost e.g., standby cost during outbreaks.
[72 empty] | bp pay from 1 Sep'20: |  | 121824.6579 | bar: 12 to 10
[21 empty] | IDR PORTION | Contract Rev.0; Dec-2019 - Mar-2021 (16 months) | [15 empty] | Contract Rev.1; Dec-2019 - Oct-2022 (19 months extension) | [18 empty] | Contract Rev.2; Dec-2019 - Jun-2023 (8 months extension)
[28 empty] | Contract is effective before start of the reimbursable period (1-Sep-2020) | [17 empty] | Extension is required to support the completion of remaining piping works.
[28 empty] | Contract covers equipment and operator/driver/manpower to support piping works carried out by Daewoo | [17 empty] | Additional Riggers to support piping activity at Train-3
Additional 22 Riggers from Feb-2020 to Aug-2020
Additional 17 Riggers from Sep-2020 to Feb-2021
1) Reflect actual spend + estimate to complete
[28 empty] | 1) Estimated Manpower/Operator: |  |  |  | 1770 | man-month | [12 empty] | 1) Reflect actual spend + estimate to complete
[28 empty] | 2) Estimated Equipment: |  |  |  | 311 | unit | [12 empty] | 2) Reflect actual spend + estimate to complete | [20 empty] | 2) Reflect actual spend + estimate to complete
[72 empty] | bp pay from 1 Sep'20: |  | 9528.6934 | bar: 12 to 10
[11 empty] | 9: TOTAL payment from 1 Sep'20: |  |  | 131353.3512
in thousand USD
2 years working under COVID protocol
Estimated start date of FGRS RCE
26-Aug-16 Contract Effective Date (ED)
1-May-19
Start of LOGI Reimbursable
23-Jul-19
AMD-2
26-Jun-20 Original PAC
1-Sep-20
Start of FGRS Reimbursable
7-May-21
AMD-3
7-Apr-22 AMD-4
5-Sep-22 AMD-5
31-Aug-21 PAC - AMD2
31-Mar-22 PAC - AMD3
21-Nov-22 PAC - AMD4
8-Jul-23 PAC - AMD5
FGRS RCE started earlier in the consideration of COVID-19 pandemic
1-Aug-23 Actual PAC
9-Apr-24 Successful PAT
13-Sep-23 LNG 1st Drop
11-month Plan Avg. 4.6% vs. Actual Avg. 4.7%
8-month Plan Avg 1.7% vs Actual Avg. 1.6%
4-month Avg.: 0.1%
9-month Plan Avg. 3.9% vs Actual Avg. 1%
11-month Plan Avg. 3.5% vs Actual Avg. 3.3%
4-month Avg.: 0.1%
9-month Plan Avg. 0.9% vs Actual Avg.: 1%
Covers COVID impact from Mar'20
Covers FM impact
Include Demobilization
8-month Plan Avg. 4.2% vs Actual Avg. 4.8%
12-month Plan Avg. 2% vs Actual Avg. 2.1%
12-month Plan Avg. 1.1% vs Actual Avg. 1.3%
12-month Plan Avg. 0.8% vs Actual Avg. 0.8%
11-month Plan Avg. 3.6% vs Actual Avg. 2.5%
8-month Plan Avg. 4.1% vs Actual Avg. 7.2%
4-month Avg.: 0.1%
9-month Plan Avg. 0.9% vs Actual Avg.: 0.5%
Rev.0; 18.5 MUSD
Rev.1; Cumm. 30 MUSD
Rev.2; Cumm. 36 MUSD --> Rev.3; Cumm. 34 MUSD
Rev.4; Cumm. 48.6 MUSD
Rev.0; 47 MUSD
Rev.1; Cumm. 53 MUSD --> Rev.2; Cumm. 63.4 MUSD
Rev.3; Cumm. 69.9 MUSD
Rev.0; 53.8 + 0.8 = 54.6 MUSD
Rev.1; Cumm. 138.8 + 11.8 = 150.6 MUSD
Rev.2; Cumm. 165.7 + 13.4 = 179.1 MUSD
- Extend completion date from 8-Mar-21 to 31-Oct-21 - Include additional scope related to Train 3 Warm Section Area and Degreasing
- Incentive for workers incl.night shift workers (1.9 MUSD)
- Additional mobilization cost (11 MUSD)
- Procurement Services for WPS and WQT from Migas (1 MUSD)
- Milestone (2.6 MUSD)
- Extend completion date from 31-Oct-21 to 30-Jun-23 - Include inconnel bolt replacement, commissioning support, KIV modification/installation, leak test support
- Include COVID impact cost (14.3 MUSD)
- Additional mobilization cost (3 MUSD)
- Extend completion date from 20-Nov-20 to 30-Sep-22 - Include EOT claim settlement (9.9 MUSD), milestone incentives (2 MUSD), standby claim (1.1 MUSD)
- Include PP35/2021 provision sum (1 MUSD)
- Include COVID impact cost (12.1 MUSD)
- Extend completion date from 30-Sep-22 to 31-May-23 - Compensation change to time rate basis
- Include updated COVID cost (3.7 MUSD)
- Extend completion date to 14-Apr-21
- Merge with steel structure installation contract (3.4 MUSD)
- Extend completion date from 14-Apr-21 to 30-Sep-22 - Include EOT claim settlement (3.3 MUSD)
- Include new milstone payment: project management support (1 MUSD)
- Additional volume of painting touch up for butt joints and support to pipe&structure (1.8 MUSD)
- Include COVID impact cost (4 MUSD)
- Extend completion date from 30-Sep-22 to 31-May-23
- Include PP35/2021 provisional sum (0.7 MUSD) - Include temporary pipe spools and support for steam blowing (0.5 MUSD
- include scope transfer from PMMJO for steel structural work at ORF (1.1 MUSD)
Rev.0; 18.5 MUSD
Rev.0; 47 MUSD
Rev.0; 53.8 + 0.8 = 54.6 MUSD
Rev.4; Cumm. 72.4 MUSD --> Rev.5; Cumm. 74.9 MUSD
Note on BY43: VOWD (up to May'24 + ETC (up to Dec'24)
Note on BY49: VOWD (up to May'24 + ETC (up to Dec'24)
Note on C126: both Daewoo USD and IDR contracts

## Overall
|  | 2016 | [6 empty] | 2017 | 2018 | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 - 12 | 1 - 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 - 3 | 4 - 6 | 7 - 9 | 10-12
|  | Before COVID-19 | [8 empty] | 3: COVID-19 Pandemic; 12: FM
EPCI Contract Key Dates
CONTRACT VALUE TRANSFORMATION | ORIGINAL |  |  |  | LUMP SUM 2,396 MUSD
PROV SUM 36 MUSD
| AMD-2 |  |  |  | LUMP SUM (incl.LOGI) | [5 empty] | 5: LUMP SUM (excl.LOGI); TOTAL LUMP SUM 2,667 MUSD; 11: FGRS RCE 188 MUSD; 9: Demobilization
PROV SUM 36 MUSD
LOGI RCE 250 MUSD
| AMD-3 |  |  |  | LUMP SUM (incl.LOGI) | [5 empty] | 5: LUMP SUM (excl.LOGI); TOTAL LUMP SUM 2,643 MUSD; 9: FGRS RCE 421 MUSD; 4: Demobilization
LOGI RCE 310 MUSD
PROV SUM 273 MUSD (incl. COVID Response 236 MUSD)
Backcharge on Fuel Equipment -20 MUSD
| AMD-4 |  |  |  | LUMP SUM (incl.LOGI) | [5 empty] | 5: LUMP SUM (excl.LOGI); TOTAL LUMP SUM 2,643 MUSD; 9: FGRS RCE 854 MUSD; 12: Demobilization |  |  |  |  | 2016-08-26
[11 empty] | 5: LOGI RCE 342 MUSD |  |  |  |  | 2020-06-26
PROV SUM 445 MUSD (incl. COVID Response 408 MUSD)
Backcharge on Fuel Equipment -20 MUSD
| AMD-5 |  |  |  | LUMP SUM (incl.LOGI) | [5 empty] | 5: LUMP SUM (excl.LOGI); TOTAL LUMP SUM 2,643 MUSD; 9: FGRS RCE 1,510 MUSD; 7: Demobilization
LOGI RCE 447 MUSD
PROV SUM 467 MUSD (incl. COVID Response 420 MUSD)
Backcharge on Fuel Equipment -20 MUSD
| Post AMD-5 |  |  |  | LUMP SUM (incl.LOGI) | [5 empty] | 5: LUMP SUM (excl.LOGI); TOTAL LUMP SUM 2,643 MUSD; 9: FGRS RCE 1,830 MUSD
LOGI RCE 479 MUSD
PROV SUM 478 MUSD (incl. COVID Response 420 MUSD)
Backcharge on Fuel Equipment -20 MUSD
FGRS RCE ACTUAL COST (MUSD) | Monthly FGRS | [29 empty] | 30.9822 | 43.6446 | 39.3792 | 18.9942 | 6.0915 | 15.3404 | 30.9037 | 37.3978 | 40.0561 | 36.6476 | 19.8232 | 19.7288 | 32.2243 | 40.7959 | 44.945 | 44.9286 | 54.1167 | 55.0453 | 63.6219 | 56.2193 | 60.4038 | 64.216 | 70.561 | 74.2649 | 84.3162 | 63.1108 | 67.4946 | 65.4731 | 43.2187 | 42.671 | 45.0574 | 45.7958 | 38.1297 | 45.1744 | 39.5462 | 25.5767 | 22.953 | 18.5404 | 27.9157 | 24.0577 | 137.3576
| AMD-3 Est.Period | [9 empty] | 9: FGRS RCE 675 MUSD
| AMD-4 Est.Period | [9 empty] | 9: FGRS RCE 1215
| AMD-5 Est.Period | [9 empty] | 9: FGRS RCE 1,541
| Post AMD-5 | [9 empty] | 9: Cummulative FGRS RCE (VOWD+ETC): 1,837
LOGI RCE ACTUAL COST (MUSD) | Monhtly LOGI | [13 empty] | 15.5064 | 33.9983 | 54.47 | 76.816 | 100.3709 | 124.3829 | 145.5246 | 167.155 | 186.663 | 205.1683 | 221.8566 | 234.1767 | 242.2351 | 250.9905 | 257.5128 | 262.793 | 271.7151 | 276.0313 | 282.7341 | 287.6285 | 291.3234 | 295.2016 | 300.1043 | 304.2904 | 309.0379 | 312.9942 | 317.0333 | 320.9884 | 324.7843 | 328.1075 | 333.015 | 337.185 | 341.6393 | 346.5465 | 351.0386 | 355.4068 | 360.5549 | 364.5682 | 368.587 | 372.3528 | 377.396 | 381.5854 | 385.9058 | 390.2703 | 394.7417 | 399.3178 | 403.6695 | 406.5956 | 410.7717 | 414.7493 | 418.4999 | 422.2413 | 425.6643 | 429.4673 | 434.2991 | 438.9036 | 42.7639
| AMD-3 Est.Period | [9 empty] | 5: LOGI RCE 351 MUSD
| AMD-4 Est.Period | [9 empty] | 5: LOGI RCE 386 MUSD
| AMD-5 Est.Period | [9 empty] | 5: LOGI RCE 415 MUSD
| Post AMD-5 | [9 empty] | 5: Cummulative LOGI RCE (VOWD+ETC): 482 MUSD |  |  |  | --> increase due to vessel extension from Jun'24 to Sep'24
Estimated start date of FGRS RCE
26-Aug-16 Contract Effective Date (ED)
1-May-19
Start of LOGI Reimbursable
23-Jul-19
AMD-2
26-Jun-20 Original PAC
1-Sep-20
Start of FGRS Reimbursable
7-May-21
AMD-3
7-Apr-22 AMD-4
5-Sep-22 AMD-5
31-Aug-21 PAC - AMD2
31-Mar-22 PAC - AMD3
21-Nov-22 PAC - AMD4
8-Jul-23 PAC - AMD5
FGRS RCE started earlier in the consideration of COVID-19 pandemic
1-Aug-23 Actual PAC
9-Apr-24 Successful PAT
13-Sep-23 LNG 1st Drop
Include Demobilization
Covers FM impact
2nd Outbreak
Note on BY43: VOWD (up to May'24 + ETC (up to Dec'24)
Note on BY49: VOWD (up to May'24 + ETC (up to Dec'24)